| Appendix A: Initiative #1: Create and/or Enhance Organizational Policies and Procedures to best serve people with disabilities who have experience sexual violence |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| June-September 2012 |  |  |  |  |  |  |
|  | Who is Responsible? |  | Timeline (Months) |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Short Term |  |  |  |
|  |  |  | J12 | J12 | A12 | S12 |
| Create a policy/procedure work group |  |  | 1 | 2 | 3 | 4 |
| Develop criteria for work group |  |  | X |  |  |  |
| Develop outline of roles/responsibilities for work group |  |  | X |  |  |  |
| Identify and select members of work group from SEAL agencies |  |  | X |  |  |  |
| Recruit work group members |  |  | X |  |  |  |
| Develop orientation for work group |  |  | X |  |  |  |
| Deliver orientation for work group |  |  | X |  |  |  |
| Evaluate and enhance existing policies/procedures at SEAL agencies |  |  |  |  |  |  |
| Develop list of existing policies/procedures at SEAL agencies (reference against proposed list for change) |  |  | x |  |  |  |
| Gather existing policies/procedures from SEAL agencies |  |  | X |  |  |  |
| Create tool to analyze effectiveness and develop criteria for enhancement of existing policies/procedures using best practices from disability and sexual violence fields |  |  |  | X |  |  |
| Clarify and review any legal requirements regarding policies/procedures with SEAL agencies |  |  |  | X |  |  |
| Review and evaluate current policies/procedures using tool |  |  |  | X |  |  |
| Revise/enhance existing policies/procedures |  |  |  | X |  |  |
| Vet revised/enhanced policies/procedures through key decision makers in SEAL organizations |  |  |  |  | X |  |
| Revise policies/procedures if necessary |  |  |  |  | X |  |
| Finalize and gain approval from key decision makers in SEAL organizations |  |  |  |  | X |  |
| Send to OVW for approval |  |  |  |  |  | X |
| Develop new policies/procedures to address needs and gaps at SEAL agencies |  |  |  |  |  |  |
| Develop list of needed policies/procedures based on what gaps exist (reference against proposed list for change) |  |  | X |  |  |  |
| Utilize policy/procedure tool created for existent policy/procedure evaluation and enhancement and apply criteria to developing new policy/procedures |  |  |  | X |  |  |
| Clarify and review any legal requirements regarding policies/procedures with SEAL agencies |  |  |  | X |  |  |
| Applying the tool, draft new policies/procedures |  |  |  |  | X |  |
| Vet policies/procedures through key decision makers in SEAL organizations |  |  |  |  | X |  |
| Revise policies/procedures if necessary |  |  |  |  | X |  |
| Finalize and gain approval from key decision makers in SEAL organizations |  |  |  |  | X |  |
| Send to OVW for approval |  |  |  |  |  | X |

| Appendix A: Initiative #1: Create and/or Enhance Organizational Policies and Procedures to best serve people with disabilities who have experience sexual violence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| October 2012-September 2013 | Who is Responsible? |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Mid-Term |
|  |  |  | O12 | N12 | D12 | J13 | F13 | M13 | A13 | M13 | J13 | J13 | A13 | S13 |
|  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| Roll-Out new and enhanced policies/procedures at SEAL agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop training to support policy/procedure roll-out |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Schedule and deliver trainings |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Create mechanism for evaluation and feedback loop |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Develop process for ongoing training |  |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Tailor policy/procedures from LaFASA for local sexual assault centers in pilot sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tailor policy/procedure tools developed to consider key criteria for pilot sites |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Applying the tool, tailor LaFASA policies/procedures for each pilot site |  |  |  |  |  |  |  |  | x |  |  |  |  |  |
| Vet policies/procedures through key decision makers (if necessary) in each pilot site |  |  |  |  |  |  |  |  |  | x |  |  |  |  |
| Revise policies/procedures if necessary |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| Finalize and gain approval from key decision makers in pilot site organizations |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| Send to OVW for approval |  |  |  |  |  |  |  |  |  |  |  | x |  |  |
| Roll-Out new and enhanced policies/procedures in local sexual assault centers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop training to support policy/procedure roll-out |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Schedule and deliver trainings |  |  |  |  |  |  |  |  |  |  |  |  |  | x |
| Create mechanism for evaluation and feedback loop |  |  |  |  |  |  |  |  |  |  |  |  |  | x |
| Develop process for ongoing training |  |  |  |  |  |  |  |  |  |  |  |  |  | x |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |

| Appendix B: Initiative #2: Enhance Organizational Environments (physical, attitudinal, communication and programmatic) to provide safe, welcoming and accessible services to people with disabilities who have experience sexual violence |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| June-September 2012 |  |  |  |  |  |  |
|  | Who is Responsible? |  | Timeline (Months) |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Short Term |
|  |  |  | J12 | J12 | A12 | S12 |
| Create a safety and access work group |  |  | 1 | 2 | 3 | 4 |
| Develop criteria for work group |  |  | X |  |  |  |
| Develop outline of roles/responsibilities for work group |  |  | X |  |  |  |
| Identify and select members of work group from SEAL agencies; pilot sites (and people with disabilities and survivors) |  |  | X |  |  |  |
| Recruit work group members |  |  | X |  |  |  |
| Develop orientation for work group |  |  | X |  |  |  |
| Deliver orientation for work group |  |  | X |  |  |  |
| Conduct safety, welcoming and access reviews at SEAL agencies and pilot site locations |  |  |  |  |  |  |
| Gather existent tools used for safety and access reviews |  |  |  | X |  |  |
| Determine which tool best suits SEAL |  |  |  | X |  |  |
| Train work group to conduct reviews |  |  |  | X |  |  |
| Schedule review with liaison and disseminate pre-site survey/assessment |  |  |  | x |  |  |
| Conduct reviews |  |  |  | x | x |  |
| Develop report of findings of assessment, and plans for removal of barriers (physical, programmatic, attitudinal, and communication) |  |  |  |  |  |  |
| Debrief reviews following assessments |  |  |  | x | X |  |
| Analyze findings |  |  |  | x | X |  |
| Prioritize findings - short/mid/long term |  |  |  |  | X |  |
| Write Reports |  |  |  |  | X | x |
| Share with key decision makers at SEAL agencies for input |  |  |  |  | X | x |
| Revise report if necessary |  |  |  |  | x | x |
| Create a plan for implementation of proposed changes |  |  |  |  |  | X |
| Submit to OVW for approval |  |  |  |  |  | X |
| Begin implementation |  |  |  |  |  | X |

| Appendix B: Initiative #2: Enhance Organizational Environments (physical, attitudinal, communication and programmatic) to provide safe, welcoming and accessible services to people with disabilities who have experience sexual violence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| October 2012-September 2013 | Who is Responsible? |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Mid-Term |
|  |  |  | O12 | N12 | D12 | J13 | F13 | M13 | A13 | M13 | J13 | J13 | A13 | S13 |
|  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| Develop new tool to be used in rural programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Utilizing experience of conducting reviews at local pilot site organizations, adapt current tool to better assess rural programs |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Revise tool if necessary |  |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Send to OVW for approval |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Conduct safety, welcoming and access reviews at sexual assault center pilot sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Schedule review with liaison and disseminate pre-site survey/assessment |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Debrief reviews following assessments |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Analyze findings |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Prioritize findings - short/mid/long term |  |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Write reports |  |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Share with key decision makers at pilot sites |  |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Revise report if necessary |  |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Create a plan for implementation of proposed changes |  |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Submit to OVW |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Begin implementation |  |  |  |  |  |  |  |  |  |  | X |  |  |  |

| Appendix C: Initiative #3: Build Capacity of Organizations, and Direct Service staff for working at the intersection of sexual violence and people with disabilities (knowledge; skills; comfort; confidence) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| October 2012-September 2013 | Who is Responsible? |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Mid-Term |
|  |  |  | O12 | N12 | D12 | J13 | F13 | M13 | A13 | M13 | J13 | J13 | A13 | S13 |
| Create a knowledge building work group |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| Develop criteria for work group |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Develop outline of roles/responsibilities for work group |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Identify and select members of work group from SEAL agencies and pilot sites |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Recruit work group members |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Develop orientation for work group |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Deliver orientation for work group |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Build organizational knowledge of SEAL partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify current trainings that are being delivered |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Develop criteria for assessing current trainings |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Assess, evaluate, and identify gaps in current trainings using criteria |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Create and/or enhance training curriculum |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Vet new/enhanced training curriculum through key decision makers in SEAL organizations |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Revise new/enhanced training curriculum if necessary |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Finalize and gain approval from key decision makers in SEAL organizations |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Create training plans/process |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Create mechanisms for evaluation and feedback |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Submit training package (curriculum, etc.) to OVW for approval |  |  |  |  |  |  |  |  | x |  |  |  |  |  |
| Schedule and deliver trainings |  |  |  |  |  |  |  |  |  | X | x |  |  |  |
| Create process of ongoing trainings |  |  |  |  |  |  |  |  |  |  |  | X |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Build organizational knowledge of local pilot sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tailor SEAL partner training package for rural communities |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Vet local pilot site training package through key decision makers in pilot sites |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Revise local pilot site training package if necessary |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Finalize and gain approval from key decision makers in pilot sites |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Create training plans/process |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Create mechanism for evaluation and feedback |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Submit local pilot site/rural training package (curriculum, etc.) to OVW for approval |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Schedule and deliver trainings |  |  |  |  |  |  |  |  |  |  |  |  |  | x |
| Create process of ongoing trainings |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

| Appendix D: Initiative #4: Enhance Organizational Relationships and Capacity to Collaborate at the State and Local levels |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| June-September 2012 |  |  |  |  |  |  |
|  | Who is Responsible? |  | Timeline (Months) |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Short Term |
|  |  |  | J12 | J12 | A12 | S12 |
| Create a work group |  |  | 1 | 2 | 3 | 4 |
| Develop criteria for work group |  |  | X |  |  |  |
| Develop outline of roles/responsibilities for work group |  |  | X |  |  |  |
| Identify and select members of work group from SEAL agencies and pilot sites |  |  | X |  |  |  |
| Recruit work group members |  |  | X |  |  |  |
| Develop orientation for work group |  |  | X |  |  |  |
| Build capacity to collaborate within pilot sites |  |  |  |  |  |  |
| Create process and engage pilot sites (structured meetings; agendas; collaboration building activities |  |  |  | x |  |  |
| Facilitate/develop criteria for meaningful participation in local collaborations (development of pilot site collaboration charters, etc.) |  |  |  |  | x |  |
| Develop tool kit for development of pilot site collaborations |  |  |  |  | x |  |
| Send to OVW for approval |  |  |  |  | X |  |
| Facilitate on-going activities in local collaboratives |  |  |  |  |  | X |

| Appendix D: Initiative #4: Enhance Organizational Relationships and Capacity to Collaborate at the State and Local levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| October 2012-September 2013 | Who is Responsible? |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiative/Activities | SEAL Team | Work Group | Mid-Term |
|  |  |  | O12 | N12 | D12 | J13 | F13 | M13 | A13 | M13 | J13 | J13 | A13 | S13 |
| Strengthen and formalize relationships between SEAL organizations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create mechanism to share training opportunities within SEAL agencies |  |  |  |  |  | x | x |  |  |  |  |  |  |  |
| Develop MOUs for sustainability of relationships between SEAL partner agencies |  |  |  |  |  |  |  | x | x |  |  |  |  |  |
| Create/develop/investigate opportunities for deepening and sustaining relationships between SEAL partner agencies. |  |  |  |  |  |  |  |  |  | x | x | x | x | x |
| Build capacity to collaborate within pilot sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create process and engage pilot sites (structured meetings; agendas; collaboration building activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate/develop criteria for meaningful participation in local collaborations (development of pilot site collaboration charters, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop tool kit for development of pilot site collaborations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send to OVW for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate on-going activities in local collaboratives |  |  | x | x | x | x | x | x | x | x | x | x | x | x |